## Table 5-1 (10-Yr)
Lower St. Croix Partnership Annual Plan of Work (based on LSC CWMP Table 5-1)
# | Activity | Priority Location | Measurable Output | Implementation Actions | Years 1-2 Outputs | Years 1-2 Estimated Cost | Year 1 Outputs Accomplished | Year 1 Dollars Spent | Years 3 ‐ 4 Outputs | Years 3 ‐ 4 Estimated Cost | Years 5 ‐ 6 Outputs | Years 5 ‐ 6 Estimated Cost | Years 7 ‐ 8 Outputs | Years 7 ‐ 8 Estimated Cost | Years 9 ‐ 10 Outputs | Years 9 ‐ 10 Estimated Cost | 10‐year Estimated Cost
Part A. Implementation Actions for Agricultural Lands
1 | GW Quality (Table 3‐1 GW1A, 2B) | Basin Wide Priority ‐ Agricultural lands where: 1) DWSMA vulnerability is moderate, high, or very high; or 2) Pollution sensitivity to wells is high or very high; or 3) Pollution sensitivity to near surface materials is karst or high; or 4) Well testing show ≥ 5 mg/L nitrate See Figure 5‐1 | Install BMPs on 2,200 acres that improve soil health and/or reduce nitrogen and pesticide pollution to groundwater |  | 300 ac |  |  |  | 400 ac |  | 500 ac |  | 500 ac |  | 500 ac
2 | Rivers & Streams + St. Croix River WQ (Table 3‐1 R&S 1A; STC 1B, C) | Regionally Significant Rivers and Streams: - All streams and tributaries in Sunrise River Watershed (whole watershed regardless of direct drainage) - Direct drainage areas to St. Croix River through Rock, Rush, Goose, Lawrence, and Browns Creeks and Trout Brook and other small streams shown in Figure 5‐2 See Table 5‐2 for streams and total phosphorus reduction goals; see Figure 5‐2 | Reduce total phosphorus by 3,300 lbs/year (install approximately 220 BMPs @ estimated 15 lbs/BMP) and reduce TSS, bacteria, and nitrogen as secondary benefit |  | 450 lbs TP (approx. 30 BMPs) |  |  |  | 600 lbs TP (approx. 40 BMPs) |  | 750 lbs TP (approx. 50 BMPs) |  | 750 lbs TP (approx. 50 BMPs) |  | 750 lbs TP (approx. 50 BMPs)
3 | Lake WQ from ag (Table 3‐1 LK1A, 2A) | Regionally Significant Lakes for Agricultural BMPs See Table 5‐3 for lakes and total phosphorus reduction goals; see Figure 5‐3 for map | Install conservation BMPs, near sensitive lakes or in direct lake catchments to reduce TP by 1,275 lbs (estimated 15 lbs/BMP) and to reduce TSS, bacteria, and nitrogen as secondary benefit |  | 150 lbs TP (approx.300 ac and/or 10 BMPs) |  |  |  | 225 lbs TP (approx. 400 ac and/or 15 BMPs) |  | 300 lbs TP (approx. 500 ac and/or 20 BMPs) |  | 300 lbs TP (approx. 500 ac and/or 20 BMPs) |  | 300 lbs TP (approx. 500 ac and/or 20 BMPs)
4 | GW Quantity (Table 3‐1 GW2A) | All agricultural irrigators; highest priority given to highest consumers [For context: Active water use permits from MPARS database 2018: 100 agricultural irrigators; 157 Water Supply Wells; 37 Non‐crop irrigators. Total = 294. 100 of those used >1MG in 2018.] | Install or retrofit smart technology on 40 irrigation systems | [5 empty] | 10 systems |  | 10 systems |  | 10 systems |  | 10 systems
5 | River & Stream Flows (Table 3‐1 R&S 3A) | Basin wide | Identify and map 100% of private ditches as part of developing Conservation Plans |  | Maps created during all applicable landowner interactions
6 | Drainage impacts on wetlands (Table 3‐1 WTL 1B) | All public and private ditches | Review 100% of drainage projects for possible impacts to wetland quality |  | All active and proposed projects reviewed
7 | Drainage impact on rivers & streams (Table 3‐1 R&S 1C) | Judicial and public ditches | Maintain or improve downstream water quality following ditch maintenance |  | No negative change in downstream water quality
8 | GW quality from contaminants (Table 3‐1 GW1B) | Priority areas: Where pollution sensitivity to near surface materials is high, or in karst areas, or where bedrock is at or near the surface; see Figure 1‐3 for map Secondary priority: Basin wide | Upgrade 100 non‐conforming or non‐ compliant SSTS to properly functioning, compliant systems. [For context: Estimated 4,202 SSTS basin wide failing to protect GW. Source: SSTS Annual Report 2018 (MPCA, Aug 2019) Number of SSTS per county * % of county in LSC * estimated 15% of SSTS failing to protect groundwater statewide] |  | 20 systems |  |  |  | 20 systems |  | 20 systems |  | 20 systems |  | 20 systems
9 | Lake impacts from SSTS (Table 3‐1 LK 1C) | Basin wide: Shorelands adjacent to nutrient impaired lakes Chisago Co: Countywide | Basin wide: Decrease non‐compliant and non‐conforming SSTS in shorelands adjacent to nutrient impaired lakes Chisago Co: Decrease non‐compliant and non‐conforming SSTS in all areas by 50% and in shorelands adjacent to nutrient impaired lakes by 80% [For context: Estimated 5,323 non‐compliant SSTS basin wide. Source: SSTS Annual Report 2018 (MPCA, Aug 2019): Number of SSTS per county * % of county in LSC * estimated 19% of SSTS non‐compliant statewide] |  | 20 systems |  |  |  | 20 systems |  | 20 systems |  | 20 systems |  | 20 systems
10 | GW quality from contaminants (Table 3‐1 GW1B) | Basin wide | Properly seal or floodproof 100% of known or discovered abandoned wells or wells at risk of flooding |  | 100% of known and discovered abandoned wells are sealed
SUBTOTAL: Part A. Implementation Actions for Agricultural Lands (Part A does not assign dollar amounts to numbered line items)
Part B. Implementation for Developed and Developing Lands
11 | GW recharge & infiltration (Table 3‐1 GW 2B) + Lake & stream WQ (Table 3‐1 LK1B, R&S 1A) | Basin wide [Estimated 40 communities in basin without MIDS or similar standards] | Implement Minimal Impact Design Standards or more restrictive in 20 communities; including climate resiliency provisions or standards | [7 empty] | 10 LGUs |  | 10 LGUs
12 | GW recharge & stream flow (Table 3‐1 GW 2B, R&S 3A) | In critical groundwater recharge areas as identified in existing or future maps or studies | Retrofit 20 existing developments with infiltration, recharge and reuse projects |  | 4 projects |  |  |  | 4 projects |  | 4 projects |  | 4 projects |  | 4 projects
13 | St. Croix River flows (Table 3‐1 STC 3A) | Direct catchments to the St. Croix River and Lake St. Croix | Evaluate and update small storm volume control and large storm rate control ordinances in 4 communities | [7 empty] | 2 LGUs |  | 2 LGUs
14 | St. Croix River + Rivers & streams WQ (Table 3‐1 STC 1B; R&S 1A) | Regionally Significant Rivers and Streams: - All streams and tributaries in Sunrise River Watershed (whole watershed regardless of direct drainage) - Direct drainage areas to St. Croix River through Rock, Rush, Goose, Lawrence, and Browns Creeks and Trout Brook and other small streams shown in Figure 5‐2 See Table 5‐2 for streams and total phosphorus reduction goals; See Figure 5‐2 | Reduce TP by 100 lbs. (approximately 100 BMPs) and reduce TSS, bacteria, and nitrogen as secondary benefit [Assume 1 lb/BMP; typical reduction for raingarden or similar BMP] |  | 20 lbs TP (approx. 20 BMPs) |  |  |  | 20 lbs TP (approx. 20 BMPs) |  | 20 lbs TP (approx. 20 BMPs) |  | 20 lbs TP (approx. 20 BMPs) |  | 20 lbs TP (approx. 20 BMPs)
15 | Lake WQ (Table 3‐1 LK 1B) | Regionally Significant Lakes for Urban BMPs See Table 5‐3 for lakes and total phosphorus reduction goals; See Figure 5‐3 | Reduce TP by 100 lbs. (approximately 100 BMPs) and reduce TSS, bacteria, and nitrogen as secondary benefit [Assume 1 lb/BMP; typical reduction for raingarden or similar BMP] |  | 20 lbs TP (approx. 20 BMPs) |  |  |  | 20 lbs TP (approx. 20 BMPs) |  | 20 lbs TP (approx. 20 BMPs) |  | 20 lbs TP (approx. 20 BMPs) |  | 20 lbs TP (approx. 20 BMPs)
16 | St. Croix River chlorides (Table 3‐1 STC 1D) | Basin wide | 75% of all cities have staff certified in MPCA’s Level 1 and Level 2 Smart Salting Training |  | Total of 15% of cities |  |  |  | Total of 30% of cities |  | Total of 45% of cities |  | Total of 60% of cities |  | Total of 75% of cities
17 | GW quantity (Table 3‐1 GW 2A) | All irrigators; highest priority given to highest consumers and communities with highest residential usage | Install or retrofit smart technology on 40 irrigation systems | [5 empty] | 20 systems |  | 20 systems
18 | GW contaminants (Table 3‐1 GW 1B) | Basin wide ‐ all currently unlicensed facilities and generators | License 100% of hazardous waste generators |  | Figures depend on number of generators identified
19 | GW contaminants (Table 3‐1 GW 1B) | Priority areas: Where pollution sensitivity to near surface materials is high, or in karst areas, or where bedrock is at or near the surface Secondary priority: Basin wide | Upgrade non‐conforming or non‐compliant SSTS to properly functioning, compliant systems. [See Line 8 of this table for context.] |  | [Covered under Table 5‐1, Part A #8]
20 | Lake impacts from SSTS (Table 3‐1 LK 1C) | Basin wide: Shorelands adjacent to nutrient impaired lakes Chisago Co: Countywide | Basin wide: Decrease non‐compliant and non‐ conforming SSTS in shorelands adjacent to nutrient impaired lakes Chisago Co: Decrease non‐compliant and non‐ conforming SSTS in all areas by 50% and in shorelands adjacent to nutrient impaired lakes by 80% [See Line 10 of this table for context.] |  | [Covered under Table 5‐1, Part A #9]
21 | Lake shorelines (Table 3‐1 LK 2B & UP 2A) | Regionally Significant Lakes for Protection and Sustainable Development: Table 5‐3 and Figure 5‐3 | Install 100 shoreline restoration projects [100% of lakeshore owners with altered shorelines are provided information on restoration programs] |  | 20 projects |  |  |  | 20 projects |  | 20 projects |  | 20 projects |  | 20 projects
22 | Protect wetlands (Table 3‐1 WTL 1A) | Basin wide during land use change or alteration, development or redevelopment | Increase by 5 the number of LGUs with adopted wetland protections including buffer requirements and setbacks for permanent structures |  | 1 LGU |  |  |  | 1 LGU |  | 1 LGU |  | 1 LGU |  | 1 LGU
23 | Maintain & restore habitat (Table 3‐1 UP 1F) | Land with priority habitats and corridor connections | 10% of land in new developments is dedicated to wildlife habitat [significant new areas of land conversion from vacant or rural land to residential, commercial/industrial, institutional, or transportation] |  | 10% of land in new dev. |  |  |  | 10% of land in new develop |  | 10% of land in new develop |  | 10% of land in new develop |  | 10% of land in new develop
24 | Sensitive lake protection (Table 3‐1 LK 2A) | Regionally Significant Lakes for Protection and Sustainable Development: Table 5‐3 and Figure 5‐3 | Implement sustainable development and land preservation programs in lakesheds of priority lakes through 10 easements or acquisitions |  | 2 easements or acquisitions |  |  |  | 2 easements or acquisition |  | 2 easements or acquisition |  | 2 easements or acquisition |  | 2 easements or acquisition
25 | Landlocked basin impact on River (Table 3‐1 STC 1B, 3A, 4C) | Eutrophic natural landlocked basins to be discharged to St. Croix River | Perform analysis and implement measures to meet state standards for nutrients on 3 waterbodies |  | 2 basins |  |  |  | 1 basin
SUBTOTAL: Part B. Implementation for Developed and Developing Lands (Part B does not assign dollar amounts to numbered line items)
Part C. Implementation for Ecosystem Services
26 | Rivers & Streams ecosyste ms & flow (Table 3‐1 R&S 2A, 3A, STC 1B) | St. Croix River and Lake St. Croix direct drainage tributaries | Reduce TP loading and TSS loading by 425 lbs and 1,085 tons, respectively. Implement 5 stream restoration projects to restore and improve stream corridors, instream habitat, and riparian area stability [Average TP reduction/restoration = 85 lbs; Average TSS reduction/restoration = 217 tons] |  | 1 stream resto project |  |  |  | 1 stream resto project |  | 1 stream resto project |  | 1 stream resto project |  | 1 stream resto project
27 | Trout populations (Table 3‐1 R&S 1B) | Trout streams (Brown's Creek, Valley Creek, Lawrence Creek, Trout Brook, Willow Brooke, Mill Stream, Falls Creek, Gilbertsons’s Creek) | Trout populations maintained through stream restorations, BMP installations, and enforcement of development standards | [5 empty] | Year 3: All streams trout YOY recruit‐ ment, survival of previous year class |  | Year 6: All streams trout YOY recruit‐ ment, survival of previous year class |  |  |  | Year 9: All streams trout YOY recruit‐ ment, survival of previous year class
28 | Wetland quantity (Table 3‐1 WTL 2A, 2B) | 1. In highest priority catchments (red, yellow and green areas) within BWSR’s Compensation Planning Framework priority catchments in the Lower St. Croix River Watershed (Figure 5‐5) 2. In locations where studies or mapping tools find that restoration will have significant positive impact on natural resources. | Create or restore 1,000 acres of historic wetlands lost to land use changes |  | 200 acres created or restored |  |  |  | 200 acres created or restored |  | 200 acres created or restored |  | 200 acres created or restored |  | 200 acres created or restored
29 | Wetland loss (Table 3‐1 WTL 2A, 1B) | Judicial and public ditches | Mitigate loss of wetland acres resulting from ditch maintenance activities |  | No net wetland loss |  |  |  | No net wetland loss |  | No net wetland loss |  | No net wetland loss |  | No net wetland loss
30 | Wetland quantity (Table 3‐1 WTL 2B) | Basin wide | Create and maintain 2 new BWSR and USACE approved wetland banks within the basin |  | 1 new wetland bank | [7 empty] | 1 new wetland bank
31 | AIS in Lakes & St. Croix River (Table 3‐1 LK 2C; STC 2A) | High traffic boat launches on St. Croix River and Lake St. Croix | Increase watercraft inspection hours by 25% |  | Increase hours by 5% |  |  |  | Increase hours by 5% |  | Increase hours by 5% |  | Increase hours by 5% |  | Increase hours by 5%
32 | AIS (Table 3‐1 LK 2C; STC 2A; R&S 2B) | Within 15 miles of all public boat launches on zebra mussel infested lakes and rivers | Within 15 miles of all public boat launches on zebra mussel infested lakes and rivers |  | 2 new decon stations | [7 empty] | 2 new decon stations
33 | AIS signs (Table 3‐1 LK 2C; STC 2A; R&S 2B) | Basin wide | Install AIS informational signage at 20 boat launches and marinas |  | 4 new launches w/ signage |  |  |  | 4 new launches w/ signage |  | 4 new launches w/ signage |  | 4 new launches w/ signage |  | 4 new launches w/ signage
34 | AIS in Lakes (Table 3‐1 LK 2C) | Lakes in Chisago Co. and Isanti Co. with public access | Develop 1 comprehensive AIS rapid response plan for lakes |  | 1 comprehensive AIS rapid response plan developed
35 | Phragmites (Table 3‐1 WTL 1C) | In order of priority 1. Chisago Lakes LID 2. Carlos Avery WMA 3. Elsewhere in Chisago Co and Isanti Co 4. Headwaters of North Branch & West Branch Sunrise River | Reduce the size and number of invasive phragmites locations as reported on EddMaps by 50% or 45 infestation areas. Stabilize and eradicate those small infestataions less than 1,000 – 2,000 sq. ft. through rapid response plans, where available |  | Reduce by 9 infestations |  |  |  | Reduce by 9 infestation |  | Reduce by 9 infestation |  | Reduce by 9 infestation |  | Reduce by 9 infestation
36 | Lake levels (Table 3‐1 LK 3A) | Chisago Co. Lakes = Chisago Lakes Chain of Lakes (Chisago, South Lindstrom, North Lindstrom, Green, Little Green, North Center, South Center), Fish, Horseshoe, Little Horseshoe, Sunrise | Develop resiliency plans or responses, such as a Slow‐No‐Wake Ordinance or Channel and Weir Operations and Maintenance Plans, to address vulnerable properties |  | Review and modify existing plans
37 | Internal loading (Table 3‐1 LK 1D) | In lakes where internal loading is estimated to be a significant contributor to degraded water quality and where not addressing the internal loading would result in sustained degradation (See Internal Loading Lakes Table 5‐4) | Address source of internal loading 3 in lakes | [7 empty] | 1 study implement ed |  | 1 study implement ed |  | 1 study implemen ted
38 | Shoreland (Table 3‐1 UP 1A, R&S 2A, LK 2B) | Basin wide | Increase the number of LGUs (including counties) by 2 that adopt innovative shoreland standards | [5 empty] | 1 new LGU w/ adopted standards |  | 1 new LGU w/ adopted standards
39 | Resilient lands (Table 3‐1 UP 1C, 1D) | Private lands in priority corridors and critical habitat areas and large‐scale developments with land‐use change | Increase in the number of diverse landscape designs and plantings resilient to climate change |  | 4 designs |  |  |  | 4 designs |  | 4 designs |  | 4 designs |  | 4 designs
40 | Land protection (Table 3‐1 UP 1B; R&S 2A; LK 2A) | First priority: Areas near already protected lands (public or private), tributaries near impaired waters, areas where known endangered species are present and identified biologically significant natural areas as identified by MLCCS mapping Second priority: Basin wide | At least 1000 acres protected through acquisition and easements. |  | 200 acres protected |  |  |  | 200 acres protected |  | 200 acres protected |  | 200 acres protected |  | 200 acres protected
41 | Land protection (Table 3‐1 UP 1C, LK 1B) | First priority: Areas where upland habitat is fractured and shoreline areas where there is high to moderate development or land under future development pressure Second priority: Basin wide | Create 20 new Landscape Stewardship Plans |  | 4 new plans |  |  |  | 4 new plans |  | 4 new plans |  | 4 new plans |  | 4 new plans
42 | Habitat improve (Table 3‐1 UP 2C) | Basin wide based on prioritized mapping including MLCCS maps and other critical habitat mapping | 1,000 new acres managed for better habitat, or as recommended in Landscape Stewardship Plans |  | 200 new acres managed |  |  |  | 200 new acres managed |  | 200 new acres managed |  | 200 new acres managed |  | 200 new acres managed
43 | Protected lands (Table 3‐1 UP 2B) | Areas located along bluffland or adjacent to publicly owned forest land such as state parks and trails | Increase acres under private Forest Management Plans or Woodland Stewardship Plans by 20% [23 plans over 10 years] |  | 4 new plans developed |  |  |  | 4 new plans developed |  | 4 new plans developed |  | 4 new plans developed |  | 7 new plans developed
SUBTOTAL: Part C. Implementation for Ecosystem Services (Part C does not assign dollar amounts to numbered line items)
Part D. Implementation for Prioritization and Analysis: Issues, Goals, Actions, Measurable Outputs, and Priority Locations
44 | STC 1A | Basin wide | Evaluate the water quality metrics, set reporting standards, report on goal progress for the St. Croix River | Identify, appoint, and empower entity or person to lead/evaluate the water quality metrics, set reporting standards, report on goal progress. |  | 50000 |  |  |  | 50000 |  | 50000 |  | 50000 |  | 50000 | 250000
45 | GW 3A | Order of Priority: 1) Surrounding known contamination sites where data are lacking 2) DWSMAs 3) Townships without nitrate testing 4) Basin wide | Pollution sources (including mines), areas around chemical contamination sites, vulnerable areas, and surface water‐GW interactions are studied and mapped | Work with State agencies and Metropolitan Council to study and map pollution sources (including mines), areas around chemical contamination sites, vulnerable areas, and surface water‐GW interactions |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 100000 | 100000
46 | GW 3A | Basin wide | 100% of recharge areas and groundwatersheds of GW dependent natural resources are mapped | Support agencies such as DNR and Met Council in mapping recharge areas and groundwatersheds of GW dependent natural resources |  | 0 |  |  |  | 40000 |  | 40000 |  | 10000 |  | 0 | 90000
47 | GW 3A | Basin wide where needed | Complete at least one county groundwater plan | Build on existing GRAPS to develop groundwater plans that lay out technical framework, issues, policies and implementation actions for the protection and conservation of groundwater resources. |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 100000 | 100000
48 | GW 3A | Maintain basin wide; expand in Isanti and Pine Co. 1) DWSMAs 2) Groundwatersheds of GW‐dependent natural resources | Maintain existing or increase number of new observation wells | Work with MnDNR to maintain and expand observation well program |  | 83730 |  |  |  | 83730 |  | 83730 |  | 83730 |  | 83730 | 418650
49 | LK 1D | Regionally Significant Lakes for Internal Loading Analyses Table 5‐4 | Calculate internal loading of phosphorus | Calculate internal loading of phosphorus on 15 lakes @ $25,000 each |  | 75000 |  |  |  | 75000 |  | 75000 |  | 75000 |  | 75000 | 375000
50 | LK 4A | Anoka Co. Lakes = Pet, Rice, South Coon, Skunk, Tamarack Chisago Co. Lakes = Sunrise, Little Horseshoe Isanti Co. Lakes = Hoffman, Horseleg, Horseshoe, Upper and Lower birch, East and West Twin, Tamarack (30‐ 0001‐00), Long (30‐0002‐ 00,) Big Pine (30‐0015‐00), Grass (30‐0017‐00), Splittstoeser (30‐00041‐00) | Baseline data such as transparency, total phosphorus and chlorophyll‐ a are collected | Develop monitoring plan and collect data using available means such as volunteers, Met Council's CAMP, MPCA's citizen monitoring program, MPCA's Intensive watershed monitoring program, SWCDs, counties, parks departments, lake associations, etc. Anoka Co annual costs (5 lakes * $2,100/lake) = $10,500 Chisago Co annual costs (2 lakes) = $1,200 Isanti Co annual costs (12 lakes) = $1,430/lake = $17,160 |  | 57720 |  |  |  | 57720 |  | 57720 |  | 57720 |  | 57720 | 288600
51 | LK 4A STC 2B, 4C | Basin wide | Participate in studies and/or stay informed of latest science to assess the impact of a changing climate on lakes and the St. Croix River | Use latest climate science to implement adaptive management | Included in existing work |  |  |  | Included in existing work |  | Included in existing work | [5 empty] | 0
52 | LK 4A | Chisago Chain of Lakes | 100% of lakes prone to anthropogenic water level variation are identified | Manage the channel and weir system with an approved operation and maintenance plan. |  | 72000 |  |  |  | 72000 |  | 72000 |  | 72000 |  | 72000 | 360000
53 | LK 4A | Basin wide | 100% of lakes prone to direct anthropogenic water level variation are identified | Participate in DNR lake level monitoring program to routinely collect lake level data |  | 26000 |  |  |  | 26000 |  | 26000 |  | 26000 |  | 26000 | 130000
54 | LK 1A, 1B, 4A | Subwatersheds of Regionally Significant Lakes Table 5‐3 and Figure 5‐3 | 20 subwatershed project targeting analyses are completed (estimated $10,000‐$50,000/SWA or $30,000 ave) | Conduct analyses to identify and prioritize water quality improvement projects within a priority subwatershed. Methods and analyses can include site or field scale subwatershed analyses, diagnostic monitoring, spatial analysis and | 5 SWAs | 150000 |  |  | 5 SWAs | 150000 | 4 SWAs | 120000 | 3 SWAs | 90000 | 3 SWAs | 90000 | 600000
55 | R&S 1A, STC 4B | Regionally Significant Rivers and Streams: - Streams and tributaries in Sunrise R. Watershed - Direct drainage areas to St. Croix River through Rock, Rush, Goose, and Browns Creeks and Trout Brook and other small streams as shown in Table 5‐2 and Figure 5‐2. | 20 subwatershed project targeting analyses are completed (estimated $10,000 ‐ $50,000/SWA or $30,000 ave) | mapping, modeling, cost benefit analyses, or other data‐driven targeting activities. See Section VII.B. for further description. | 5 SWAs | 150000 |  |  | 5 SWAs | 150000 | 4 SWAs | 120000 | 3 SWAs | 90000 | 3 SWAs | 90000 | 600000
56 | STC 4A, 4C | Tributaries to the St. Croix | Coordinated hydrologic, chemical, and biological monitoring of the St. Croix River and its tributaries; nutrient loading data of major tributaries to the St. Croix River is evaluated. | Operate up to 10 new monitoring stations that lack data (quality and quantity) to evaluate progress toward achieving the TMDL and to identify priority subwatersheds. @ $10,000/year/station |  | 100000 |  |  |  | 200000 |  | 200000 |  | 200000 |  | 200000 | 900000
57 | STC 3A | Land use authorities in the St. Croix Riverway. | Evaluate the floodplain and zoning ordinances for consistency and effectiveness in protecting the floodplain function and preventing flood damages. Include impacts of variances in the evaluation. | Work with land use authorities along St. Croix River and MnDNR Area Hydrologists to evaluate floodplain and zoning ordinances and update where appropriate. |  | 50000 |  |  |  | 50000 |  | 50000 |  | 50000 |  | 50000 | 250000
58 | STC 4B & UP 2A | Intermittent and perennial tributaries and watercourses flowing directly to St. Croix River | Inventory and prioritize active erosion sites. | Identify, evaluate, and rank active gullies directly discharging into the St. Croix or its tributaries [LIDAR to identify gully locations; RUSLE & BWSR pollution reduction calculator to determine pollution reduction numbers] |  | 50000 |  |  |  | 50000 |  | 50000 |  | 50000 |  | 50000 | 250000
59 | STC 2B, 4C UP 1A | Basin wide | Map priority restoration and protection areas for acquisition, easements, and voluntary stewardship | Complete level 4/5 MLCCS basin wide. Expand the Washington County Natural Resource Framework and use their methodology in Anoka, Chisago, Isanti, and Pine Counties. (MLCCS = $1,000/sq mi * 640 sq miles) |  | 240000 |  |  |  | 200000 |  | 200000 |  | 0 |  | 0 | 640000
60 | UP 1E | First priority: Public lands or near public lands; areas may be further prioritized thru cooperative weed mgmt area Second priority: Basin wide | Map and target "eradicate and control list" invasive species populations for each county Contact 50% of landowners for species on restricted list | Implement a cooperative weed management area (including MNDOT when possible) and promote associated implementation strategies. |  | 0 |  |  |  | 0 |  | 100000 |  | 100000 |  | 0 | 200000
61 | WTL 3E | Pine County | Complete soil survey | Complete soil survey as developed by NRCS, USDA & shown in Soil Survey Geographic (SSURGO) Database | To be completed by NRCS |  |  |  | To be completed by NRCS |  | To be completed by NRCS |  | To be completed by NRCS |  | To be completed by NRCS |  | 0
62 | WTL 3D | Wetlands upstream of nutrient impaired streams and lakes | Monitor 10 identified wetlands for nutrient and volume contribution to impaired lakes and streams | Use subwatershed analyses or monitoring/modeling data to identify degraded wetlands with the potential of contributing high nutrient loads to downstream resources. |  | 150000 |  |  |  | 150000 |  | 150000 |  | 150000 |  | 150000 | 750000
63 | WTL 3D | Basin wide | Identify 5 degraded wetlands with best restoration potential in each HUC 10 | Use existing Restorable Wetland Prioritization Tool to focus effort | To be completed in conjunction with existing activities |  |  |  | To be completed in conjunction with existing activities |  | To be completed in conjunction with existing activities |  | To be completed in conjunction with existing activities |  | To be completed in conjunction with existing activities | 0 | 0
64 | WTL 3E & 1D | 1st priority: Public ditches in Isanti Co. 2nd priority: Basin wide | Obtain Nutrient Loading Data in basins/wetlands near Ditch outlets to identify areas for ditch improvements to filter runoff | Collect water quality data near ditch outlets of 25 ditches (estimated $2,000 per ditch) |  | 10000 |  |  |  | 10000 |  | 10000 |  | 10000 |  | 10000 | 50000
65 | WTL 3A, 3B, 3C | 1st Priority: Isanti County 2nd Priority: Basin wide | Create wetland inventory based on MLCCS, and function and value assessment and/or floristic quality assessment | Increase by 5 the number of LGUs with policies requiring wetland function and value assessments with project proposals such as developments or ditch work. |  | 20000 |  |  |  | 50000 |  | 50000 |  | 0 |  | 0 | 120000
66 | WTL 3B | Pine County and Isanti County | An inventory and map of all areas of wetland loss and historic wetlands is locally verified | Verify recently completed inventory and map % of areas of wetland loss and historic wetlands |  | 12000 |  |  |  | 12000 |  | 12000 |  | 12000 |  | 12000 | 60000
SUBTOTAL: Part D. Implementation for Prioritization and Analysis: Issues, Goals, Actions, Measurable Outputs, and Priority Locations
TOTAL: Table 5-1 Parts A, B, C, D
Activity Abbreviations
GW = Groundwater
R&S = Rivers & Streams
LK = Lakes
WTL = Wetlands
UP = Upland Habitat
STC = St. Croix River & Lake St. Croix
AIS = Aquatic Invasive Species
SSTS = Subsurface Sewage Treatment Systems
WQ = Water Quality

## 2024 Workplan
Lower St. Croix Partnership DRAFT 2024 Annual Plan of Work (based on LSC CWMP Table 5-1)
| Gray cells = overarching activities from Table 5-1 | Orange cells = proposed new activity numbers that go beyond existing WBIF activity numbers: A11 Aquatic Invasive Species Prevention & Management A12 Land Acquisition & Management A13 Shoreland Protection & Management A14 Ditch Law A15 Interagency Coordination
# | Activity | Priority Location | Measurable Output | Implementation Actions | Years 1-2 Outputs | Years 1-2 Estimated Cost | Year 1 Outputs Accomplished | Year 1 Dollars Spent | Years 3 ‐ 4 Outputs | 2024 Estimated Outputs | 2024 Estimated Cost | 23WBIF Activity Categories | Years 5 ‐ 6 Outputs | Years 5 ‐ 6 Estimated Cost | Years 7 ‐ 8 Outputs | Years 7 ‐ 8 Estimated Cost | Years 9 ‐ 10 Outputs | Years 9 ‐ 10 Estimated Cost | 10‐year Estimated Cost
Part A. Implementation Actions for Agricultural Lands
| Shared Services: Agronomy Outreach Specialist | [9 empty] | 125000 | A5 Ag Outreach
| Cost Share for Agricultural BMPs (structural and non-structural) | [9 empty] | 470000 | A1 + A3 Structural and Non-structural Ag BMPs
| Conservation planning and technical assistance | [9 empty] | 273900 | A7 Technical/Engineering
1 | GW Quality (Table 3‐1 GW1A, 2B) | Basin Wide Priority ‐ Agricultural lands where: 1) DWSMA vulnerability is moderate, high, or very high; or 2) Pollution sensitivity to wells is high or very high; or 3) Pollution sensitivity to near surface materials is karst or high; or 4) Well testing show ≥ 5 mg/L nitrate See Figure 5‐1 | Install BMPs on 2,200 acres that improve soil health and/or reduce nitrogen and pesticide pollution to groundwater |  | 300 ac |  |  |  | 400 ac | 200 ac |  | A3 Ag Non-structural BMPs | 500 ac |  | 500 ac |  | 500 ac
2 | Rivers & Streams + St. Croix River WQ (Table 3‐1 R&S 1A; STC 1B, C) | Regionally Significant Rivers and Streams: - All streams and tributaries in Sunrise River Watershed (whole watershed regardless of direct drainage) - Direct drainage areas to St. Croix River through Rock, Rush, Goose, Lawrence, and Browns Creeks and Trout Brook and other small streams shown in Figure 5‐2 See Table 5‐2 for streams and total phosphorus reduction goals; see Figure 5‐2 | Reduce total phosphorus by 3,300 lbs/year (install approximately 220 BMPs @ estimated 15 lbs/BMP) and reduce TSS, bacteria, and nitrogen as secondary benefit |  | 450 lbs TP (approx. 30 BMPs) |  |  |  | 600 lbs TP (approx. 40 BMPs) | 300 lbs TP (approx. 20 BMPs) |  | A1 Ag Structural BMPs | 750 lbs TP (approx. 50 BMPs) |  | 750 lbs TP (approx. 50 BMPs) |  | 750 lbs TP (approx. 50 BMPs)
3 | Lake WQ from ag (Table 3‐1 LK1A, 2A) | Regionally Significant Lakes for Agricultural BMPs See Table 5‐3 for lakes and total phosphorus reduction goals; see Figure 5‐3 for map | Install conservation BMPs, near sensitive lakes or in direct lake catchments to reduce TP by 1,275 lbs (estimated 15 lbs/BMP) and to reduce TSS, bacteria, and nitrogen as secondary benefit |  | 150 lbs TP (approx.300 ac and/or 10 BMPs) |  |  |  | 225 lbs TP (approx. 400 ac and/or 15 BMPs) | 112.5 lbs TP (approx. 200 ac) |  | A1 Ag Structural BMPs | 300 lbs TP (approx. 500 ac and/or 20 BMPs) |  | 300 lbs TP (approx. 500 ac and/or 20 BMPs) |  | 300 lbs TP (approx. 500 ac and/or 20 BMPs)
4 | GW Quantity (Table 3‐1 GW2A) | All agricultural irrigators; highest priority given to highest consumers [For context: Active water use permits from MPARS database 2018: 100 agricultural irrigators; 157 Water Supply Wells; 37 Non‐crop irrigators. Total = 294. 100 of those used >1MG in 2018.] | Install or retrofit smart technology on 40 irrigation systems | [5 empty] | 10 systems | 5 systems | 72500 | A3 Non-structural Ag BMPs | 10 systems |  | 10 systems |  | 10 systems
5 | River & Stream Flows (Table 3‐1 R&S 3A) | Basin wide | Identify and map 100% of private ditches as part of developing Conservation Plans |  | Maps created during all applicable landowner interactions | [6 empty] | A7 Technical/Engineering
| Develop and implement plan for management and maintenance of ditch system including a system and protocol for establishing BMPs within easement right of ways of existing public ditches. | [9 empty] | 5000 | A14 Ditch Law
| Provide training for local staff on topics related to drainage management, wetland management, and related areas | [9 empty] | 500 | A6 + A5 Shared Services Education and Ag outreach
6 | Drainage impacts on wetlands (Table 3‐1 WTL 1B) | All public and private ditches | Review 100% of drainage projects for possible impacts to wetland quality |  | All active and proposed projects reviewed | [5 empty] | 17000 | A14 Ditch Law
7 | Drainage impact on rivers & streams (Table 3‐1 R&S 1C) | Judicial and public ditches | Maintain or improve downstream water quality following ditch maintenance |  | No negative change in downstream water quality | [6 empty] | A14 Ditch Law
8 | GW quality from contaminants (Table 3‐1 GW1B) | Priority areas: Where pollution sensitivity to near surface materials is high, or in karst areas, or where bedrock is at or near the surface; see Figure 1‐3 for map Secondary priority: Basin wide | Upgrade 100 non‐conforming or non‐ compliant SSTS to properly functioning, compliant systems. [For context: Estimated 4,202 SSTS basin wide failing to protect GW. Source: SSTS Annual Report 2018 (MPCA, Aug 2019) Number of SSTS per county * % of county in LSC * estimated 15% of SSTS failing to protect groundwater statewide] |  | 20 systems |  |  |  | 20 systems | 10 systems | 270000 | A3 Ag Non-structural BMPs | 20 systems |  | 20 systems |  | 20 systems
9 | Lake impacts from SSTS (Table 3‐1 LK 1C) | Basin wide: Shorelands adjacent to nutrient impaired lakes Chisago Co: Countywide | Basin wide: Decrease non‐compliant and non‐conforming SSTS in shorelands adjacent to nutrient impaired lakes Chisago Co: Decrease non‐compliant and non‐conforming SSTS in all areas by 50% and in shorelands adjacent to nutrient impaired lakes by 80% [For context: Estimated 5,323 non‐compliant SSTS basin wide. Source: SSTS Annual Report 2018 (MPCA, Aug 2019): Number of SSTS per county * % of county in LSC * estimated 19% of SSTS non‐compliant statewide] |  | 20 systems |  |  |  | 20 systems | 10 systems |  | A3 Ag Non-structural BMPs | 20 systems |  | 20 systems |  | 20 systems
10 | GW quality from contaminants (Table 3‐1 GW1B) | Basin wide | Properly seal or floodproof 100% of known or discovered abandoned wells or wells at risk of flooding |  | 100% of known and discovered abandoned wells are sealed | [6 empty] | A3 Non-structural Ag BMPs
SUBTOTAL: Part A. Implementation Actions for Agricultural Lands (Part A does not assign dollar amounts to numbered line items)
Part B. Implementation for Developed and Developing Lands
| Shared Services: Educator 1) Provide outreach, education and ordinance development on Minimal Impact Design Standards with local governments, developers, and others; 2) Facilitate shared education and outreach program across basin to provide education; engage residents, businesses, and local officials; and promote and market programs and practices. | [9 empty] | 110000 | A6 Shared Educator
| Cost Share for Urban BMPs (structural and non-structural) | [9 empty] | 300000 | A2 + A3 Urban Structural and Non-structural BMPs
| Provide project reviews and technical assistance on stormwater management and urban best management practices through local staff and local initiatives including evaluating small storm volume control and large storm rate control ordinances. | [9 empty] | 250800 | A7 Technical/Engineering
11 | GW recharge & infiltration (Table 3‐1 GW 2B) + Lake & stream WQ (Table 3‐1 LK1B, R&S 1A) | Basin wide [Estimated 40 communities in basin without MIDS or similar standards] | Implement Minimal Impact Design Standards or more restrictive in 20 communities; including climate resiliency provisions or standards | [6 empty] | 0 | 0 | A6 Shared Services Education | 10 LGUs |  | 10 LGUs
12 | GW recharge & stream flow (Table 3‐1 GW 2B, R&S 3A) | In critical groundwater recharge areas as identified in existing or future maps or studies | Retrofit 20 existing developments with infiltration, recharge and reuse projects |  | 4 projects |  |  |  | 4 projects | 2 projects |  | A2 Structural Urban BMPs | 4 projects |  | 4 projects |  | 4 projects
13 | St. Croix River flows (Table 3‐1 STC 3A) | Direct catchments to the St. Croix River and Lake St. Croix | Evaluate and update small storm volume control and large storm rate control ordinances in 4 communities | [8 empty] | A15 Interagency Coordination | 2 LGUs |  | 2 LGUs
14 | St. Croix River + Rivers & streams WQ (Table 3‐1 STC 1B; R&S 1A) | Regionally Significant Rivers and Streams: - All streams and tributaries in Sunrise River Watershed (whole watershed regardless of direct drainage) - Direct drainage areas to St. Croix River through Rock, Rush, Goose, Lawrence, and Browns Creeks and Trout Brook and other small streams shown in Figure 5‐2 See Table 5‐2 for streams and total phosphorus reduction goals; See Figure 5‐2 | Reduce TP by 100 lbs. (approximately 100 BMPs) and reduce TSS, bacteria, and nitrogen as secondary benefit [Assume 1 lb/BMP; typical reduction for raingarden or similar BMP] |  | 20 lbs TP (approx. 20 BMPs) |  |  |  | 20 lbs TP (approx. 20 BMPs) | 10 lbs. TP (approx. 10 BMPs) |  | A2 Structural Urban BMPs | 20 lbs TP (approx. 20 BMPs) |  | 20 lbs TP (approx. 20 BMPs) |  | 20 lbs TP (approx. 20 BMPs)
15 | Lake WQ (Table 3‐1 LK 1B) | Regionally Significant Lakes for Urban BMPs See Table 5‐3 for lakes and total phosphorus reduction goals; See Figure 5‐3 | Reduce TP by 100 lbs. (approximately 100 BMPs) and reduce TSS, bacteria, and nitrogen as secondary benefit [Assume 1 lb/BMP; typical reduction for raingarden or similar BMP] |  | 20 lbs TP (approx. 20 BMPs) |  |  |  | 20 lbs TP (approx. 20 BMPs) | 10 lbs. TP (approx. 10 BMPs) |  | A2 Structural Urban BMPs | 20 lbs TP (approx. 20 BMPs) |  | 20 lbs TP (approx. 20 BMPs) |  | 20 lbs TP (approx. 20 BMPs)
16 | St. Croix River chlorides (Table 3‐1 STC 1D) | Basin wide | 75% of all cities have staff certified in MPCA’s Level 1 and Level 2 Smart Salting Training |  | Total of 15% of cities |  |  |  | Total of 30% of cities | Total of 15% of cities |  | A15 Interagency Coordination | Total of 45% of cities |  | Total of 60% of cities |  | Total of 75% of cities
17 | GW quantity (Table 3‐1 GW 2A) | All irrigators; highest priority given to highest consumers and communities with highest residential usage | Install or retrofit smart technology on 40 irrigation systems | [5 empty] | 20 systems | 10 systems | 145000 | A2 Structural Urban BMPs | 20 systems
18 | GW contaminants (Table 3‐1 GW 1B) | Basin wide ‐ all currently unlicensed facilities and generators | License 100% of hazardous waste generators |  | Figures depend on number of generators identified | [6 empty] | A15 Interagency Coordination
19 | GW contaminants (Table 3‐1 GW 1B) | Priority areas: Where pollution sensitivity to near surface materials is high, or in karst areas, or where bedrock is at or near the surface Secondary priority: Basin wide | Upgrade non‐conforming or non‐compliant SSTS to properly functioning, compliant systems. [See Line 8 of this table for context.] |  | [Covered under Table 5‐1, Part A #8] | [6 empty] | A3 Urban Non-Structural BMPs
20 | Lake impacts from SSTS (Table 3‐1 LK 1C) | Basin wide: Shorelands adjacent to nutrient impaired lakes Chisago Co: Countywide | Basin wide: Decrease non‐compliant and non‐ conforming SSTS in shorelands adjacent to nutrient impaired lakes Chisago Co: Decrease non‐compliant and non‐ conforming SSTS in all areas by 50% and in shorelands adjacent to nutrient impaired lakes by 80% [See Line 10 of this table for context.] |  | [Covered under Table 5‐1, Part A #9] | [6 empty] | A3 Urban Non-Structural BMPs
21 | Lake shorelines (Table 3‐1 LK 2B & UP 2A) | Regionally Significant Lakes for Protection and Sustainable Development: Table 5‐3 and Figure 5‐3 | Install 100 shoreline restoration projects [100% of lakeshore owners with altered shorelines are provided information on restoration programs] |  | 20 projects |  |  |  | 20 projects | 10 projects | 40000 | A2 Structural Urban BMPs | 20 projects |  | 20 projects |  | 20 projects
22 | Protect wetlands (Table 3‐1 WTL 1A) | Basin wide during land use change or alteration, development or redevelopment | Increase by 5 the number of LGUs with adopted wetland protections including buffer requirements and setbacks for permanent structures |  | 1 LGU |  |  |  | 1 LGU | 1 LGU |  | A15 Interagency Coordination | 1 LGU |  | 1 LGU |  | 1 LGU
23 | Maintain & restore habitat (Table 3‐1 UP 1F) | Land with priority habitats and corridor connections | 10% of land in new developments is dedicated to wildlife habitat [significant new areas of land conversion from vacant or rural land to residential, commercial/industrial, institutional, or transportation] |  | 10% of land in new dev. |  |  |  | 10% of land in new develop | 5% of land in new development |  | A12 Land Acquisition & Management | 10% of land in new develop |  | 10% of land in new develop |  | 10% of land in new develop
24 | Sensitive lake protection (Table 3‐1 LK 2A) | Regionally Significant Lakes for Protection and Sustainable Development: Table 5‐3 and Figure 5‐3 | Implement sustainable development and land preservation programs in lakesheds of priority lakes through 10 easements or acquisitions |  | 2 easements or acquisitions |  |  |  | 2 easements or acquisition | 1 easement or acquistion |  | A3 Urban Non-Structural BMPs | 2 easements or acquisition |  | 2 easements or acquisition |  | 2 easements or acquisition
25 | Landlocked basin impact on River (Table 3‐1 STC 1B, 3A, 4C) | Eutrophic natural landlocked basins to be discharged to St. Croix River | Perform analysis and implement measures to meet state standards for nutrients on 3 waterbodies |  | 2 basins |  |  |  | 1 basin | 1 basin | 350000 | A7 Technical/Engineering
SUBTOTAL: Part B. Implementation for Developed and Developing Lands (Part B does not assign dollar amounts to numbered line items)
Part C. Implementation for Ecosystem Services
| Perform culvert inventory: redesign and restore as road projects are completed to help manage to natural hydrologic conditions through use of MnDNR Geomorphic Approach to infrastructure Design at Road‐Watercourse Intersections | [9 empty] | 100000 | A7 Technical/Engineering
26 | Rivers & Streams ecosyste ms & flow (Table 3‐1 R&S 2A, 3A, STC 1B) | St. Croix River and Lake St. Croix direct drainage tributaries | Reduce TP loading and TSS loading by 425 lbs and 1,085 tons, respectively. Implement 5 stream restoration projects to restore and improve stream corridors, instream habitat, and riparian area stability [Average TP reduction/restoration = 85 lbs; Average TSS reduction/restoration = 217 tons] |  | 1 stream resto project |  |  |  | 1 stream resto project | 1 stream restoration project | 350000 | A3 Ag/Urban Non-Structural BMPs | 1 stream resto project |  | 1 stream resto project |  | 1 stream resto project
27 | Trout populations (Table 3‐1 R&S 1B) | Trout streams (Brown's Creek, Valley Creek, Lawrence Creek, Trout Brook, Willow Brooke, Mill Stream, Falls Creek, Gilbertsons’s Creek) | Trout populations maintained through stream restorations, BMP installations, and enforcement of development standards | [5 empty] | Year 3: All streams trout YOY recruit‐ ment, survival of previous year class | Year 4: All streams trout YOY recruit‐ ment, survival of previous year class |  | A3 Ag/Urban Non-Structural BMPs | Year 6: All streams trout YOY recruit‐ ment, survival of previous year class |  |  |  | Year 9: All streams trout YOY recruit‐ ment, survival of previous year class
28 | Wetland quantity (Table 3‐1 WTL 2A, 2B) | 1. In highest priority catchments (red, yellow and green areas) within BWSR’s Compensation Planning Framework priority catchments in the Lower St. Croix River Watershed (Figure 5‐5) 2. In locations where studies or mapping tools find that restoration will have significant positive impact on natural resources. | Create or restore 1,000 acres of historic wetlands lost to land use changes |  | 200 acres created or restored |  |  |  | 200 acres created or restored | 100 acres created or restored | 495000 | A4 Wetland Restoration | 200 acres created or restored |  | 200 acres created or restored |  | 200 acres created or restored
29 | Wetland loss (Table 3‐1 WTL 2A, 1B) | Judicial and public ditches | Mitigate loss of wetland acres resulting from ditch maintenance activities |  | No net wetland loss |  |  |  | No net wetland loss | No net wetland loss |  | A14 Ditch Law | No net wetland loss |  | No net wetland loss |  | No net wetland loss
30 | Wetland quantity (Table 3‐1 WTL 2B) | Basin wide | Create and maintain 2 new BWSR and USACE approved wetland banks within the basin |  | 1 new wetland bank | [6 empty] | A4 Wetland Restoration |  |  | 1 new wetland bank
31 | AIS in Lakes & St. Croix River (Table 3‐1 LK 2C; STC 2A) | High traffic boat launches on St. Croix River and Lake St. Croix | Increase watercraft inspection hours by 25% |  | Increase hours by 5% |  |  |  | Increase hours by 5% | Increase hours by 2.5% | 443500 | A11 Aquatic Invasive Species Prevention & Management | Increase hours by 5% |  | Increase hours by 5% |  | Increase hours by 5%
32 | AIS (Table 3‐1 LK 2C; STC 2A; R&S 2B) | Within 15 miles of all public boat launches on zebra mussel infested lakes and rivers | Within 15 miles of all public boat launches on zebra mussel infested lakes and rivers |  | 2 new decon stations | [6 empty] | A11 Aquatic Invasive Species Prevention & Management |  |  | 2 new decon stations
33 | AIS signs (Table 3‐1 LK 2C; STC 2A; R&S 2B) | Basin wide | Install AIS informational signage at 20 boat launches and marinas |  | 4 new launches w/ signage |  |  |  | 4 new launches w/ signage | 2 new launches w/ signage |  | A11 Aquatic Invasive Species Prevention & Management | 4 new launches w/ signage |  | 4 new launches w/ signage |  | 4 new launches w/ signage
34 | AIS in Lakes (Table 3‐1 LK 2C) | Lakes in Chisago Co. and Isanti Co. with public access | Develop 1 comprehensive AIS rapid response plan for lakes |  | 1 comprehensive AIS rapid response plan developed | [6 empty] | A11 Aquatic Invasive Species Prevention & Management
35 | Phragmites (Table 3‐1 WTL 1C) | In order of priority 1. Chisago Lakes LID 2. Carlos Avery WMA 3. Elsewhere in Chisago Co and Isanti Co 4. Headwaters of North Branch & West Branch Sunrise River | Reduce the size and number of invasive phragmites locations as reported on EddMaps by 50% or 45 infestation areas. Stabilize and eradicate those small infestataions less than 1,000 – 2,000 sq. ft. through rapid response plans, where available |  | Reduce by 9 infestations |  |  |  | Reduce by 9 infestation | Reduce by 5 infestations |  | A11 Aquatic Invasive Species Prevention & Management | Reduce by 9 infestation |  | Reduce by 9 infestation |  | Reduce by 9 infestation
36 | Lake levels (Table 3‐1 LK 3A) | Chisago Co. Lakes = Chisago Lakes Chain of Lakes (Chisago, South Lindstrom, North Lindstrom, Green, Little Green, North Center, South Center), Fish, Horseshoe, Little Horseshoe, Sunrise | Develop resiliency plans or responses, such as a Slow‐No‐Wake Ordinance or Channel and Weir Operations and Maintenance Plans, to address vulnerable properties |  | Review and modify existing plans | [5 empty] | 10000 | A13 Shoreland Protection & Management
37 | Internal loading (Table 3‐1 LK 1D) | In lakes where internal loading is estimated to be a significant contributor to degraded water quality and where not addressing the internal loading would result in sustained degradation (See Internal Loading Lakes Table 5‐4) | Address source of internal loading 3 in lakes | [6 empty] | 0 | 0 | A1 + A2 + A3 Structural and Non-structural Ag/Urban BMPs | 1 study implement ed |  | 1 study implement ed |  | 1 study implemen ted
38 | Shoreland (Table 3‐1 UP 1A, R&S 2A, LK 2B) | Basin wide | Increase the number of LGUs (including counties) by 2 that adopt innovative shoreland standards | [5 empty] | 1 new LGU w/ adopted standards | 1 new LGU w/ adopted standards | 40000 | A13 Shoreland Protection & Management | 1 new LGU w/ adopted standards
39 | Resilient lands (Table 3‐1 UP 1C, 1D) | Private lands in priority corridors and critical habitat areas and large‐scale developments with land‐use change | Increase in the number of diverse landscape designs and plantings resilient to climate change |  | 4 designs |  |  |  | 4 designs | 2 designs | 50000 | A7 Technical/Engineering | 4 designs |  | 4 designs |  | 4 designs
40 | Land protection (Table 3‐1 UP 1B; R&S 2A; LK 2A) | First priority: Areas near already protected lands (public or private), tributaries near impaired waters, areas where known endangered species are present and identified biologically significant natural areas as identified by MLCCS mapping Second priority: Basin wide | At least 1000 acres protected through acquisition and easements. |  | 200 acres protected |  |  |  | 200 acres protected | 100 acres protected | 180000 | A12 Land Acquisition & Management | 200 acres protected |  | 200 acres protected |  | 200 acres protected
41 | Land protection (Table 3‐1 UP 1C, LK 1B) | First priority: Areas where upland habitat is fractured and shoreline areas where there is high to moderate development or land under future development pressure Second priority: Basin wide | Create 20 new Landscape Stewardship Plans |  | 4 new plans |  |  |  | 4 new plans | 2 new plans |  | A7 Technical/Engineering | 4 new plans |  | 4 new plans |  | 4 new plans
42 | Habitat improve (Table 3‐1 UP 2C) | Basin wide based on prioritized mapping including MLCCS maps and other critical habitat mapping | 1,000 new acres managed for better habitat, or as recommended in Landscape Stewardship Plans |  | 200 new acres managed |  |  |  | 200 new acres managed | 100 new acres managed |  | A7 Technical/Engineering | 200 new acres managed |  | 200 new acres managed |  | 200 new acres managed
43 | Protected lands (Table 3‐1 UP 2B) | Areas located along bluffland or adjacent to publicly owned forest land such as state parks and trails | Increase acres under private Forest Management Plans or Woodland Stewardship Plans by 20% [23 plans over 10 years] |  | 4 new plans developed |  |  |  | 4 new plans developed | 2 new plans developed |  | A7 Technical/Engineering | 4 new plans developed |  | 4 new plans developed |  | 7 new plans developed
SUBTOTAL: Part C. Implementation for Ecosystem Services (Part C does not assign dollar amounts to numbered line items)
Part D. Implementation for Prioritization and Analysis: Issues, Goals, Actions, Measurable Outputs, and Priority Locations
44 | STC 1A | Basin wide | Evaluate the water quality metrics, set reporting standards, report on goal progress for the St. Croix River | Identify, appoint, and empower entity or person to lead/evaluate the water quality metrics, set reporting standards, report on goal progress. |  | 50000 |  |  |  |  | 25000 | A9 Targeting Analysis |  | 50000 |  | 50000 |  | 50000 | #REF!
45 | GW 3A | Order of Priority: 1) Surrounding known contamination sites where data are lacking 2) DWSMAs 3) Townships without nitrate testing 4) Basin wide | Pollution sources (including mines), areas around chemical contamination sites, vulnerable areas, and surface water‐GW interactions are studied and mapped | Work with State agencies and Metropolitan Council to study and map pollution sources (including mines), areas around chemical contamination sites, vulnerable areas, and surface water‐GW interactions |  | 0 |  |  |  |  | 0 | A9 Targeting Analysis |  | 0 |  | 0 |  | 100000 | #REF!
46 | GW 3A | Basin wide | 100% of recharge areas and groundwatersheds of GW dependent natural resources are mapped | Support agencies such as DNR and Met Council in mapping recharge areas and groundwatersheds of GW dependent natural resources |  | 0 |  |  |  |  | 20000 | A9 Targeting Analysis |  | 40000 |  | 10000 |  | 0 | #REF!
47 | GW 3A | Basin wide where needed | Complete at least one county groundwater plan | Build on existing GRAPS to develop groundwater plans that lay out technical framework, issues, policies and implementation actions for the protection and conservation of groundwater resources. |  | 0 |  |  |  |  | 0 | A7 Technical/Engineering |  | 0 |  | 0 |  | 100000 | #REF!
48 | GW 3A | Maintain basin wide; expand in Isanti and Pine Co. 1) DWSMAs 2) Groundwatersheds of GW‐dependent natural resources | Maintain existing or increase number of new observation wells | Work with MnDNR to maintain and expand observation well program |  | 83730 |  |  |  |  | 41865 | A9 Targeting Analysis |  | 83730 |  | 83730 |  | 83730 | #REF!
49 | LK 1D | Regionally Significant Lakes for Internal Loading Analyses Table 5‐4 | Calculate internal loading of phosphorus | Calculate internal loading of phosphorus on 15 lakes @ $25,000 each |  | 75000 |  |  |  |  | 37500 | A8 Internal Analysis |  | 75000 |  | 75000 |  | 75000 | #REF!
50 | LK 4A | Anoka Co. Lakes = Pet, Rice, South Coon, Skunk, Tamarack Chisago Co. Lakes = Sunrise, Little Horseshoe Isanti Co. Lakes = Hoffman, Horseleg, Horseshoe, Upper and Lower birch, East and West Twin, Tamarack (30‐ 0001‐00), Long (30‐0002‐ 00,) Big Pine (30‐0015‐00), Grass (30‐0017‐00), Splittstoeser (30‐00041‐00) | Baseline data such as transparency, total phosphorus and chlorophyll‐ a are collected | Develop monitoring plan and collect data using available means such as volunteers, Met Council's CAMP, MPCA's citizen monitoring program, MPCA's Intensive watershed monitoring program, SWCDs, counties, parks departments, lake associations, etc. Anoka Co annual costs (5 lakes * $2,100/lake) = $10,500 Chisago Co annual costs (2 lakes) = $1,200 Isanti Co annual costs (12 lakes) = $1,430/lake = $17,160 |  | 57720 |  |  |  |  | 28860 | A9 Targeting Analysis |  | 57720 |  | 57720 |  | 57720 | #REF!
51 | LK 4A STC 2B, 4C | Basin wide | Participate in studies and/or stay informed of latest science to assess the impact of a changing climate on lakes and the St. Croix River | Use latest climate science to implement adaptive management | Included in existing work |  |  |  | Included in existing work | Included in existing work |  | A9 Targeting Analysis | Included in existing work | [5 empty] | #REF!
52 | LK 4A | Chisago Chain of Lakes | 100% of lakes prone to anthropogenic water level variation are identified | Manage the channel and weir system with an approved operation and maintenance plan. |  | 72000 |  |  |  |  | 36000 | A7 Technical/Engineering |  | 72000 |  | 72000 |  | 72000 | #REF!
53 | LK 4A | Basin wide | 100% of lakes prone to direct anthropogenic water level variation are identified | Participate in DNR lake level monitoring program to routinely collect lake level data |  | 26000 |  |  |  |  | 13000 | A7 Technical/Engineering |  | 26000 |  | 26000 |  | 26000 | #REF!
54 | LK 1A, 1B, 4A | Subwatersheds of Regionally Significant Lakes Table 5‐3 and Figure 5‐3 | 20 subwatershed project targeting analyses are completed (estimated $10,000‐$50,000/SWA or $30,000 ave) | Conduct analyses to identify and prioritize water quality improvement projects within a priority subwatershed. Methods and analyses can include site or field scale subwatershed analyses, diagnostic monitoring, spatial analysis and | 5 SWAs | 150000 |  |  | 5 SWAs | 3 SWAs | 90000 | A9 Targeting Analysis | 4 SWAs | 120000 | 3 SWAs | 90000 | 3 SWAs | 90000 | #REF!
55 | R&S 1A, STC 4B | Regionally Significant Rivers and Streams: - Streams and tributaries in Sunrise R. Watershed - Direct drainage areas to St. Croix River through Rock, Rush, Goose, and Browns Creeks and Trout Brook and other small streams as shown in Table 5‐2 and Figure 5‐2. | 20 subwatershed project targeting analyses are completed (estimated $10,000 ‐ $50,000/SWA or $30,000 ave) | mapping, modeling, cost benefit analyses, or other data‐driven targeting activities. See Section VII.B. for further description. | 5 SWAs | 150000 |  |  | 5 SWAs | 3 SWAs | 90000 | A9 Targeting Analysis | 4 SWAs | 120000 | 3 SWAs | 90000 | 3 SWAs | 90000 | #REF!
56 | STC 4A, 4C | Tributaries to the St. Croix | Coordinated hydrologic, chemical, and biological monitoring of the St. Croix River and its tributaries; nutrient loading data of major tributaries to the St. Croix River is evaluated. | Operate up to 10 new monitoring stations that lack data (quality and quantity) to evaluate progress toward achieving the TMDL and to identify priority subwatersheds. @ $10,000/year/station |  | 100000 |  |  |  |  | 100000 | A7 Technical/Engineering |  | 200000 |  | 200000 |  | 200000 | #REF!
57 | STC 3A | Land use authorities in the St. Croix Riverway. | Evaluate the floodplain and zoning ordinances for consistency and effectiveness in protecting the floodplain function and preventing flood damages. Include impacts of variances in the evaluation. | Work with land use authorities along St. Croix River and MnDNR Area Hydrologists to evaluate floodplain and zoning ordinances and update where appropriate. |  | 50000 |  |  |  |  | 25000 | A7 Technical/Engineering |  | 50000 |  | 50000 |  | 50000 | #REF!
58 | STC 4B & UP 2A | Intermittent and perennial tributaries and watercourses flowing directly to St. Croix River | Inventory and prioritize active erosion sites. | Identify, evaluate, and rank active gullies directly discharging into the St. Croix or its tributaries [LIDAR to identify gully locations; RUSLE & BWSR pollution reduction calculator to determine pollution reduction numbers] |  | 50000 |  |  |  |  | 25000 | A9 Targeting Analysis |  | 50000 |  | 50000 |  | 50000 | #REF!
59 | STC 2B, 4C UP 1A | Basin wide | Map priority restoration and protection areas for acquisition, easements, and voluntary stewardship | Complete level 4/5 MLCCS basin wide. Expand the Washington County Natural Resource Framework and use their methodology in Anoka, Chisago, Isanti, and Pine Counties. (MLCCS = $1,000/sq mi * 640 sq miles) |  | 240000 |  |  |  |  | 100000 | A9 Targeting Analysis |  | 200000 |  | 0 |  | 0 | #REF!
60 | UP 1E | First priority: Public lands or near public lands; areas may be further prioritized thru cooperative weed mgmt area Second priority: Basin wide | Map and target "eradicate and control list" invasive species populations for each county Contact 50% of landowners for species on restricted list | Implement a cooperative weed management area (including MNDOT when possible) and promote associated implementation strategies. |  | 0 |  |  |  |  | 0 | A9 Targeting Analysis |  | 100000 |  | 100000 |  | 0 | #REF!
61 | WTL 3E | Pine County | Complete soil survey | Complete soil survey as developed by NRCS, USDA & shown in Soil Survey Geographic (SSURGO) Database | To be completed by NRCS |  |  |  | To be completed by NRCS | To be completed by NRCS |  | A7 Technical/Engineering | To be completed by NRCS |  | To be completed by NRCS |  | To be completed by NRCS |  | #REF!
62 | WTL 3D | Wetlands upstream of nutrient impaired streams and lakes | Monitor 10 identified wetlands for nutrient and volume contribution to impaired lakes and streams | Use subwatershed analyses or monitoring/modeling data to identify degraded wetlands with the potential of contributing high nutrient loads to downstream resources. |  | 150000 |  |  |  |  | 75000 | A7 Technical/Engineering |  | 150000 |  | 150000 |  | 150000 | #REF!
63 | WTL 3D | Basin wide | Identify 5 degraded wetlands with best restoration potential in each HUC 10 | Use existing Restorable Wetland Prioritization Tool to focus effort | To be completed in conjunction with existing activities |  |  |  | To be completed in conjunction with existing activities | To be completed in conjunction with existing activities |  | A9 Targeting Analysis | To be completed in conjunction with existing activities |  | To be completed in conjunction with existing activities |  | To be completed in conjunction with existing activities | 0 | #REF!
64 | WTL 3E & 1D | 1st priority: Public ditches in Isanti Co. 2nd priority: Basin wide | Obtain Nutrient Loading Data in basins/wetlands near Ditch outlets to identify areas for ditch improvements to filter runoff | Collect water quality data near ditch outlets of 25 ditches (estimated $2,000 per ditch) |  | 10000 |  |  |  |  | 5000 | A9 Targeting Analysis |  | 10000 |  | 10000 |  | 10000 | #REF!
65 | WTL 3A, 3B, 3C | 1st Priority: Isanti County 2nd Priority: Basin wide | Create wetland inventory based on MLCCS, and function and value assessment and/or floristic quality assessment | Increase by 5 the number of LGUs with policies requiring wetland function and value assessments with project proposals such as developments or ditch work. |  | 20000 |  |  |  |  | 25000 | A7 Technical/Engineering |  | 50000 |  | 0 |  | 0 | #REF!
66 | WTL 3B | Pine County and Isanti County | An inventory and map of all areas of wetland loss and historic wetlands is locally verified | Verify recently completed inventory and map % of areas of wetland loss and historic wetlands |  | 12000 |  |  |  |  | 6000 | A7 Technical/Engineering |  | 12000 |  | 12000 |  | 12000 | #REF!
SUBTOTAL: Part D. Implementation for Prioritization and Analysis: Issues, Goals, Actions, Measurable Outputs, and Priority Locations
TOTAL: Table 5-1 Parts A, B, C, D
Activity Abbreviations
GW = Groundwater
R&S = Rivers & Streams
LK = Lakes
WTL = Wetlands
UP = Upland Habitat
STC = St. Croix River & Lake St. Croix
AIS = Aquatic Invasive Species
SSTS = Subsurface Sewage Treatment Systems
WQ = Water Quality